## Final Integrated Schedule
Station | Satellite | Pass_No | AOS(UTC) | LOS(UTC) | Duration_Sec | Max_Elevation | Status | Mission Activity | Remark
Svalbard | NEONSAT-1(59587) | Pass 2 | 2026-07-26 11:51:42 | 2026-07-26 12:00:21 | 518.1 | 64.2 | Allocated | [1] First Contact (TM 확인 Panel 전개 TLE update) | test1
Svalbard | NEONSAT-1A(67614) | Pass 2 | 2026-07-26 12:29:06 | 2026-07-26 12:38:10 | 543.7 | 30.77 | Allocated | [1] First Contact (TM 확인 / Panel 전개 / TLE update)
King Sejong | NEONSAT-1(59587) | Pass 3 | 2026-07-26 12:30:52 | 2026-07-26 12:37:57 | 424.2 | 17.59 | Allocated | [2] Health check (EPS / AOCS / S-band 상태 점검) | test2
Daejeon | NEONSAT-1(59587) | Pass 3 | 2026-07-26 13:11:13 | 2026-07-26 13:16:48 | 335.3 | 11.08 | Allocated | [3] Configuration check (Thermal / STX / FCS param 확인) | test3
Svalbard | NEONSAT-1(59587) | Pass 3 | 2026-07-26 13:24:32 | 2026-07-26 13:33:09 | 516.6 | 65.2 | Allocated | [4] X-band Key update (X key update)
King Sejong | NEONSAT-1(59587) | Pass 4 | 2026-07-26 14:02:21 | 2026-07-26 14:11:03 | 522 | 87.02 | Bypassed | [1차 지상 촬영] Blocked (GS King Sejong No DOWN)
Svalbard | NEONSAT-1A(67614) | Pass 3 | 2026-07-26 14:03:59 | 2026-07-26 14:13:37 | 577.8 | 63.5 | Allocated | [2] Health check (EPS / AOCS / S-band 상태 점검)
Daejeon | NEONSAT-1(59587) | Pass 4 | 2026-07-26 14:42:19 | 2026-07-26 14:50:26 | 486.8 | 32.61 | Allocated | [5] 1차 지상 촬영 (시나리오 등록 / 이미징 / 다운로드)
King Sejong | NEONSAT-1A(67614) | Pass 4 | 2026-07-26 14:43:51 | 2026-07-26 14:52:16 | 505.3 | 20.71 | Allocated | [3] Configuration check (Thermal / STX / FCS param 확인)
Svalbard | NEONSAT-1(59587) | Pass 4 | 2026-07-26 14:57:10 | 2026-07-26 15:05:34 | 504 | 43.3 | Bypassed | [1차 Cal Maneuver] Blocked (GS Svalbard No BOTH)
Daejeon | NEONSAT-1A(67614) | Pass 4 | 2026-07-26 15:25:14 | 2026-07-26 15:31:42 | 387.8 | 12.21 | Bypassed | [X-band Key update] Blocked (El Low (12.21° < 15.0°))
King Sejong | NEONSAT-1(59587) | Pass 5 | 2026-07-26 15:36:29 | 2026-07-26 15:43:22 | 413.1 | 15.61 | Bypassed | [1차 Cal Maneuver] Blocked (GS King Sejong No BOTH)
Svalbard | NEONSAT-1A(67614) | Pass 4 | 2026-07-26 15:38:42 | 2026-07-26 15:48:20 | 577.4 | 70.83 | Allocated | [4] X-band Key update (X key update)
King Sejong | NEONSAT-1A(67614) | Pass 5 | 2026-07-26 16:17:09 | 2026-07-26 16:27:10 | 600.8 | 83.63 | Bypassed | [1차 지상 촬영] Blocked (GS King Sejong No DOWN)
Svalbard | NEONSAT-1(59587) | Pass 5 | 2026-07-26 16:29:35 | 2026-07-26 16:37:55 | 500.8 | 40.3 | Bypassed | [1차 Cal Maneuver] Blocked (GS Svalbard No BOTH)
Daejeon | NEONSAT-1A(67614) | Pass 5 | 2026-07-26 16:58:02 | 2026-07-26 17:07:15 | 553.1 | 39.8 | Allocated | [5] 1차 지상 촬영 (시나리오 등록 / 이미징 / 다운로드)
Svalbard | NEONSAT-1A(67614) | Pass 5 | 2026-07-26 17:13:12 | 2026-07-26 17:22:38 | 565.3 | 48.57 | Bypassed | [1차 Cal Maneuver] Blocked (GS Svalbard No BOTH)
King Sejong | NEONSAT-1A(67614) | Pass 6 | 2026-07-26 17:53:00 | 2026-07-26 18:01:30 | 509.9 | 20 | Bypassed | [1차 Cal Maneuver] Blocked (GS King Sejong No BOTH)
Svalbard | NEONSAT-1(59587) | Pass 6 | 2026-07-26 18:01:56 | 2026-07-26 18:10:27 | 511.3 | 52.3 | Bypassed | [1차 Cal Maneuver] Blocked (GS Svalbard No BOTH)
Svalbard | NEONSAT-1A(67614) | Pass 6 | 2026-07-26 18:47:29 | 2026-07-26 18:56:51 | 561.6 | 45.21 | Bypassed | [1차 Cal Maneuver] Blocked (GS Svalbard No BOTH)
Svalbard | NEONSAT-1(59587) | Pass 7 | 2026-07-26 19:34:31 | 2026-07-26 19:43:12 | 520.8 | 88.21 | Bypassed | [1차 Cal Maneuver] Blocked (GS Svalbard No BOTH)
Svalbard | NEONSAT-1A(67614) | Pass 7 | 2026-07-26 20:21:43 | 2026-07-26 20:31:14 | 571.1 | 57.39 | Bypassed | [1차 Cal Maneuver] Blocked (GS Svalbard No BOTH)
Svalbard | NEONSAT-1(59587) | Pass 8 | 2026-07-26 21:07:41 | 2026-07-26 21:16:07 | 505.8 | 40.61 | Bypassed | [1차 Cal Maneuver] Blocked (GS Svalbard No BOTH)
Svalbard | NEONSAT-1A(67614) | Pass 8 | 2026-07-26 21:56:12 | 2026-07-26 22:05:52 | 579.4 | 85.79 | Bypassed | [1차 Cal Maneuver] Blocked (GS Svalbard No BOTH)
Svalbard | NEONSAT-1(59587) | Pass 9 | 2026-07-26 22:41:42 | 2026-07-26 22:49:06 | 444.2 | 19.32 | Bypassed | [1차 Cal Maneuver] Blocked (GS Svalbard No BOTH)
Svalbard | NEONSAT-1A(67614) | Pass 9 | 2026-07-26 23:31:17 | 2026-07-26 23:40:40 | 563.6 | 42.64 | Bypassed | [1차 Cal Maneuver] Blocked (GS Svalbard No BOTH)
Svalbard | NEONSAT-1(59587) | Pass 10 | 2026-07-27 00:16:48 | 2026-07-27 00:22:02 | 314.1 | 9.66 | Bypassed | [1차 Cal Maneuver] Blocked (El Low (9.66° < 15.0°), GS Svalbard No BOTH)
Svalbard | NEONSAT-1A(67614) | Pass 10 | 2026-07-27 01:07:14 | 2026-07-27 01:15:37 | 503 | 21.37 | Bypassed | [1차 Cal Maneuver] Blocked (GS Svalbard No BOTH)
Daejeon | NEONSAT-1(59587) | Pass 12 | 2026-07-27 02:06:36 | 2026-07-27 02:13:18 | 401.7 | 15.39 | Allocated | [6] 1차 Cal Maneuver (시나리오 등록 / Max logging / AOTM 다운)
Svalbard | NEONSAT-1A(67614) | Pass 11 | 2026-07-27 02:44:12 | 2026-07-27 02:50:36 | 383.3 | 11.32 | Bypassed | [1차 Cal Maneuver] Blocked (El Low (11.32° < 15.0°), GS Svalbard No BOTH)
King Sejong | NEONSAT-1(59587) | Pass 12 | 2026-07-27 02:46:00 | 2026-07-27 02:53:42 | 462.3 | 22.11 | Bypassed | [2차 Cal Maneuver] Blocked (GS King Sejong No BOTH)
Daejeon | NEONSAT-1(59587) | Pass 13 | 2026-07-27 03:38:53 | 2026-07-27 03:46:20 | 446.6 | 22.07 | Allocated | [7] 2차 Cal Maneuver (시나리오 등록 / Max logging / AOTM 다운)
King Sejong | NEONSAT-1(59587) | Pass 13 | 2026-07-27 04:18:33 | 2026-07-27 04:27:11 | 517.4 | 58.23 | Bypassed | [3차 Cal Maneuver] Blocked (GS King Sejong No BOTH)
Daejeon | NEONSAT-1A(67614) | Pass 13 | 2026-07-27 04:35:42 | 2026-07-27 04:44:25 | 522.6 | 25.53 | Allocated | [6] 1차 Cal Maneuver (시나리오 등록 / Max logging / AOTM 다운)
King Sejong | NEONSAT-1A(67614) | Pass 13 | 2026-07-27 05:16:12 | 2026-07-27 05:25:33 | 561.5 | 31.91 | Bypassed | [2차 Cal Maneuver] Blocked (GS King Sejong No BOTH)
King Sejong | NEONSAT-1(59587) | Pass 14 | 2026-07-27 05:51:47 | 2026-07-27 05:58:09 | 381.3 | 13.59 | Bypassed | [3차 Cal Maneuver] Blocked (El Low (13.59° < 15.0°), GS King Sejong No BOTH)
Daejeon | NEONSAT-1A(67614) | Pass 14 | 2026-07-27 06:10:28 | 2026-07-27 06:18:23 | 475.4 | 18.84 | Allocated | [7] 2차 Cal Maneuver (시나리오 등록 / Max logging / AOTM 다운)
King Sejong | NEONSAT-1A(67614) | Pass 14 | 2026-07-27 06:50:46 | 2026-07-27 07:00:30 | 584.1 | 50.11 | Bypassed | [3차 Cal Maneuver] Blocked (GS King Sejong No BOTH)
Svalbard | NEONSAT-1(59587) | Pass 15 | 2026-07-27 08:10:02 | 2026-07-27 08:15:44 | 342.6 | 10.91 | Bypassed | [3차 Cal Maneuver] Blocked (El Low (10.91° < 15.0°), GS Svalbard No BOTH)
King Sejong | NEONSAT-1A(67614) | Pass 15 | 2026-07-27 08:25:46 | 2026-07-27 08:33:06 | 440 | 14.58 | Bypassed | [3차 Cal Maneuver] Blocked (El Low (14.58° < 15.0°), GS King Sejong No BOTH)
Svalbard | NEONSAT-1(59587) | Pass 16 | 2026-07-27 09:42:59 | 2026-07-27 09:50:38 | 458.5 | 21.84 | Bypassed | [3차 Cal Maneuver] Blocked (GS Svalbard No BOTH)
Svalbard | NEONSAT-1A(67614) | Pass 16 | 2026-07-27 10:46:50 | 2026-07-27 10:54:19 | 448.7 | 15.22 | Bypassed | [3차 Cal Maneuver] Blocked (GS Svalbard No BOTH)